## Slide 1: Partnership internal communications plan
Guidance and template

## Slide 2: Internal communications -process
Identify all internal stakeholders
Evaluate their current level of awareness and engagement in the partnership objectives
Analyse their expectations regarding the partnership and its ways of working
Analyse their possible concerns regarding the partnership and its ways of working
Draw insights from stakeholder analysis
Draft plan
Validate plan
Based on the partnership objectives and stakeholder analysis,
  Define the purpose of communications
  Pick a relevant mix of different communications activities from each category (partnership status and direction, routine and engaging communications)
Fill in the internal communications plan (audience, channel, responsible person and timing)
Arrange a meeting with the core partners
Present your drafted plan and request for comments
Decide on the responsibilities and schedule for the next 6 months
Finalize the plan
Store internal communications plan and schedule in a place where everybody can access it. Share the plan with all the relevant people!
Implement plan
Include communications tasks in your own work plans
Build channels and materials
  Send calendar invitations, select meeting/celebration venues
  Decide on the meeting agendas, meeting minute structure, visual looks (e.g. partnership banner in e-Newsletter)
  Decide on feedback channels (see partner satisfaction and engagement)
Start implementing!
Follow up internal communications plan implementation
Collect feedback from partners and analyse level of engagement
Update plan accordingly
Evaluate and update

## Slide 3: Drawing insights from stakeholder analysis
Issues and objectives at stake
Key stakeholders
Primary stakeholders
Secondary stakeholders
Public sector
Private sector
Civil society
2. Primary stakeholders* – influence and motivate
Direct targeted communications
Occasional personal interaction
3. Secondary stakeholders - keep informed and interested
Close working relationship
Provide information
Show consideration and support
1. Key stakeholders – engage and collaborate
Regular two-way interaction
Direct targeted communications
Joint learning and decision-making
Personal relationships
Stakeholder prioritization helps to decide on the level of communications and engagement activities needed
Usually core partners
Usually partnership target groups
Usually non-core partners or other actors
*Nb. Partnership target groups are not internal stakeholders. Communications and engagement activities should be added to partnership implementation plan.

## Slide 4: Elements of the partnership internal communications
Ensuring engagement
Building Momentum
Establishing Routines
Partnership status and direction
Regular meetings/skype calls
Partnership status
Meeting minutes
Continuous communications
Regular meetings/skype calls
Partnership website
Social media
Success stories
Engaging communications
Field trip
Celebrations
Workshops
Increase Awareness, Alignment and Engagement
Depending on the partnership objectives and stakeholder analysis, different kind of communications activities should be planned

## Slide 5: Internal communications activity planning – some examples
Type | Channel | Description | Target audience | Timing
Partnership status and direction | Steering group meeting | Partnership overview and recent highlights Status update, risks and interdependencies Required decisions and next steps | Steering group members | Monthly
 | Email | Meeting minutes | As agreed with partners | Monthly
Routine communications | e-Newsletter | E.g. steering group greetings, upcoming activities, recent success stories, links to partnership website and social media, introduction of new partners | All partners | Monthly/Bi-monthly
 | Meeting/Skype meeting | Day-to-day implementation decisions, advice or support | Core partners | Ad hoc
Engaging communications | Lunch meeting | Unofficial meeting with focus on relationship building | Partners | Ad hoc
 | MOU signing celebration | Informal celebration (dinner or similar) | Core partners | In the end of Commit-phase
 | Strategy workshop | Member participate in a deep dive into the partnership that contains strategic planning May incorporate interactive team sessions and networking opportunities | Core partners | Annually
 | Closing ceremony |  | All partners | In the end of Act -phase
 | Field trip | Organized visit to the field | All partners | In the beginning of partnership
 | Lessons learnt workshop | Facilitated workshop | Core partners | In the scale & exit -phase

## Slide 6: Partnership internal communications - template
Reason for communications | Communications activity | Channel | Audience | Timing | Responsible | Comments
Regular status overview and agreement on upcoming tasks | Steering group meeting | Meeting | Steering group | Every 1st Friday of a month | N.N. | Standard agenda
E.g. Make sure agreed tasks are completed and followed up | Meeting minutes | Email | Core partners | Next Monday after the steering group meeting | N.N. | Standard structure
Sharing recent success stories and increasing awareness of the issues | e-Newsletter | Email | All partners, identified potential partners | January 15th, March 15th, May 15th | N.N. | Content decided in steering group meeting
Increasing engagement and celebrating success | Christmas lunch | Local restaurant | All partners | 15.12. | N.N. | Unofficial, no agenda
Make sure your internal communications plan is realistic and shared with all relevant actors